## Sheet1
S No | Activity | Assigned by | Assigned to | Assigned Date | Completion date | Status | Comments | Feedback
1 | preparing the Chef cookbook for implementing the setup of logstash within Chef-repo with the recipes of logstash_setup and logstash_config recipes Note1: Cookbook is the dedicated directory with the set of infraustructure elements which are essential for the service. Note2 : Recipes are the implemenatation section of Infraustrcture as a code for any service. | Roopa yavagal | Tulasiram Bevara |  |  | Completed | Created the chef cookbook in Chef-repo with the recipes. Note1 : all activities related to the logstash setup within the form of chef resources implemented in logstash_setup recipe. Note2: Additional and optional resources are there.
1 | Downloading RPM package for logstash to the home directory with remote_ file resource and deifned the source URL in attributes. | Roopa yavagal | Tulasiram Bevara |  |  | Completed | /usr/share/logstash-5.3.1.rpm Note:There is the Scope to define any Package version in attributes to be Installation.
2 | Installing the RPM package of the logstash with the resource of rpm_package with the property of allow_downgrade defined as true. | Roopa yavagal | Tulasiram Bevara |  |  | Completed | Installed Successfully with the Directory layout. Note: We have the provision to install the version we want with define the version in attrbutes.
3 | start the service of the logstash with the service resource and action of start and supporting reload and status put into true | Roopa yavagal | Tulasiram Bevara |  |  | Completed | Started the Service active: running Note : There is the action to define any required states of stop and restart the service with Notification in any resource and Specific Service resource.
4 | Preparing the Configuration file logstash.yml with required configurations accordingly. With the resource of the Template with the property of atomic_updation. | Roopa yavagal | Tulasiram Bevara |  |  | Completed | Replaced with the required configuration specifications. Note : since the template has atomic_update facility , we can change as per the requirement and it would be properly replaced according.
5 | Since the replacement of Configuration file , in the template resource itself restarting the service of logstash with the Notification to that service to be Restarted. | Roopa yavagal | Tulasiram Bevara |  |  | Completed | Restarted successfully the service of logstash with the required chenges applied in Configuration file logstash.yml. Active: running